## Sheet1
Related User Story | Task Description | Initial Estimate | Amount Remaining After…
|  |  | Week 1 | Week 2 | Week 3 | Week 4
view all cards in my collection | Set up the trading-card project and connect the main collection window to the card form window | 1
view the details of a card | Create the Card class with the needed card details, validation, documentation, and unit tests | 1.5
view all cards in my collection | Create and test the logic for storing cards and viewing the collection | 2
view all cards in my collection | Build the main collection window so users can view, add, edit, or remove cards | 2
add a card to my collection | Build the card form with the required fields and Save, Cancel, and Back buttons | 1.5
add a card to my collection | Add validation and saving for new cards, along with unit tests | 1.5
view the details of a card | Build the card-details view and let users return to the main collection window | 1.5
update a card in my collection | Allow users to load an existing card, make changes, and save it, then test the update logic | 1.5
remove a card from my collection | Allow users to remove a card after confirming the choice, then test the removal logic | 1
view all cards in my collection | Run mvn verify and fix any test, Checkstyle, or coverage problems until coverage reaches at least 95% | 1
| Estimate Totals | 14.5